## Product Backlog
Product Backlog
StoryID | Story name | Status | Size | Sprint | Comments
1 | A user can interact with the main window | Done | 26 | 1 | User is able to see and manipulate with user's interface
2 | User can see list of today's events | Done | 28 | 2 | Server returns a list of matches on clients request which are displayed in the user's interface
3 | User is able to filter events by type and date | Done | 23 | 3 | User can choose different criterias for a list of matches
4 | User can place bets on multiple events | Done | 15 | 4 | User can choose different matches from the pool and place a bet
5 | User can review his/her bets | Done | 12 | 4 | User can see his/her betting history
6 | Administrator can insert and edit matches | Done | 19 | 5 | New matches are added to the database and old ones are edited
7 | Administrator can set events results | Done | 7 | 5 | After the match is finished, admin can set match results in the database
8 | All tickets are evaulated according to match results | Done | 8 | 8 | Funds are added or withdrawn from the users' balance
9 | Winnings are distributed to users | Done | 2 | 8 | After all matches from the ticket have finished. Ticket result is evaulated and score is added to the winners
10 | New user is able to create an account | Done | 15 | 6 | After user fills registration form new account is stored in the system's database
11 | User is able to change information in the profile | Done | 5 | 6 | User can change information he provided during registration exclude user name
12 | User can log in with his user name and password | Done | 7 | 6 | Sign in/register functions | Planned
|  |  | 167 |  |  | Done
OnGoing
Deleted

## Release Burndown
Release Burndown Chart
Sprint | Total | Planned Work | Realized Work | Remaining Work
1 | 167 | 26 | 26 | 141
2 | 141 | 28 | 28 | 113
3 | 113 | 23 | 23 | 90
4 | 90 | 27 | 27 | 63
5 | 63 | 26 | 26 | 37
6 | 37 | 27 | 27 | 10
7 | 28 | 18 | 18 | 10
8 | 10 | 10 | 10 | 0
0
24.5714
172
1 | 147.4286
2 | 122.8571
3 | 98.2857
4 | 73.7143
5 | 49.1429
6 | 24.5714
7 | 0

## Sprint1
Sprint 1
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
26
1 | A user can interact with the main window |  | 26
1 | Make a shared interface with a test method and define the method | Stefan | 1 | 0 | 0
1 | Create the server class which rebinds implemented method from shared interface | Atanas | 3 | 0 | 0
1 | Create client class which looks up for shared interface | Atanas | 3 | 2 | 0
1 | Junit test case : test connection | Stefan | 1 | 1 | 0
1 | Create a sketch of user's main GUI | Atanas | 1 | 0 | 0
1 | Code the user's main interface | Atanas | 14 | 10 | 0
1 | Hardcode some matches | Daniel | 1 | 0 | 0
1 | Display matches in the main window | Daniel | 1 | 3 | 0
1 | Test | Daniel | 1 | 1 | 0

## Sprint2
Sprint 2
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
28
2 | User can see list of today's events |  | 28
2 | Collect all data which has to be stored in the database | Atanas | 1 | 0 | 0
2 | Develop a relational database model using normalization desing technique | Atanas | 3 | 0 | 0
2 | Document normalization process | Atanas | 1 | 1 | 0
2 | Test database functional dependencies and update anomalies | Atanas | 1 | 0 | 0
2 | Create database in postgreSQL | Atanas | 1 | 1 | 0
2 | Test : populate tables | Atanas | 1 | 1 | 0
2 | Connect java to the Database | Daniel | 2 | 0 | 0
2 | Define update method | Daniel | 1 | 0 | 0
2 | Define a SELECT method | Daniel | 1 | 1 | 0
2 | Test connection, insert and update methods | Daniel | 1 | 1 | 0
2 | Junit test case | Daniel | 1 | 1 | 0
2 | Class Data which contains information about user based on database | Stefan | 1 | 0 | 0
2 | Create class User with username, password and an instance of the Data class | Stefan | 1 | 0 | 0
2 | Class Match with all information needed | Stefan | 2 | 1 | 0
2 | Create class Bet with information about a single bet | Stefan | 1 | 1 | 0
2 | Create class Ticket which contains information about a user and an array list of bets | Stefan | 2 | 2 | 0
2 | Design how to send a list of matches over a network | Atanas | 1 | 1
2 | Create a method which takes matches from database and displays them in the JTable | Atanas | 5 | 1 | 0
2 | Test: display matches from the database in a JTable | Atanas | 1 | 1 | 0

## Sprint3
Sprint 3
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
23
3 | User can filter events by type/date |  | 23
3 | Code the query method which selects matches based on their type | Daniel | 3 | 0 | 0
3 | Test query | Daniel | 1 | 0 | 0
3 | Query method which selects matches in a given time period | Daniel | 3 | 1 | 0
3 | Validating method for wrong time periods | Atanas | 3 | 0 | 0
3 | Test select methods | Daniel | 1 | 1 | 0
3 | Design Controller class for the main GUI | Atanas | 2 | 0 | 0
3 | Add an actionListener to "Filter" button | Atanas | 4 | 2 | 0
3 | Connect queries with "Filter" button | Atanas | 4 | 4 | 0
3 | Test: check results in JTable | Stefan | 2 | 2 | 0

## Sprint4
Sprint 4
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
27
4 | User can place bets on multiple events |  | 15
4 | Design and code virtual ticket GUI | Stefan | 4 | 1 | 0
4 | Add a mouseListener to the JTable | Atanas | 3 | 0 | 0
4 | On double click, add a row to the JTable in the virtual ticket | Atanas | 1 | 1 | 0
4 | Automate adding the coefficient based on a selected column | Atanas | 1 | 1 | 0
4 | Add a button ActionListener in controller | Atanas | 1 | 1 | 0
4 | Create a ticket from selected matches | Atanas | 2 | 2 | 0
4 | Test created ticket | Atanas | 1 | 1 | 0
4 | Code the method which inserts a ticket in the database | Atanas | 1 | 1 | 0
4 | Test ticket insertion | Atanas | 1 | 1 | 0
5 | User can review his/her bets |  | 12
5 | Design and code the history interface | Daniel | 4 | 0 | 0
5 | Test: display String values in a history panel | Daniel | 1 | 0 | 0
5 | All tickets are displayed in the history tabbed pane | Daniel | 1 | 0 | 0
5 | On ticket selection, the JTable is filled with detailed information about the selected ticket | Daniel | 2 | 2 | 0
5 | Test displaying of a ticket | Daniel | 1 | 1
5 | Test displaying of ticket details | Daniel | 1 | 1 | 0
5 | Figure out how to refresh tickets and results | Daniel | 1 | 3 | 0
5 | Test refreshing | Daniel | 1 | 1 | 0

## Sprint5
Sprint 5
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
26
6 | Administrator can insert and edit matches |  | 19
6 | Draw a sketch of the admin's GUI | Stefan | 1 |  | 0
6 | Code the admin's GUI | Stefan | 5 |  | 0
6 | Design the controller for the GUI | Atanas | 1 |  | 0
6 | Design a solution about how to create a new match from inserted values | Atanas | 2 |  | 0
6 | Test the createMatch method | Atanas | 1 |  | 0
6 | Create a method which edits a match in the database | Daniel | 1
6 | Add action and table listeners | Daniel | 4 | 1 | 0
6 | Test the controller class | Daniel | 4 | 1 | 0
7 | Administrator can set events results |  | 7
7 | Connect Admin's GUI with the controller | Stefan | 1 | 1 | 0
7 | When Admin picks an event from the JTable, he can change its results, time and date. | Atanas | 2 | 2 | 0
7 | Create a validator for wrong input | Atanas | 3 | 3 | 0
7 | Test match insertion and match editing | Atanas | 1 | 1 | 0

## Sprint6
Sprint 6
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
27
10 | A new user is able to create an account |  | 15
10 | Code the method which creates a new User | Stefan | 2 | 0 | 0
10 | Create a method for inserting new users' information in the database | Stefan | 3 | 2 | 0
10 | Test insert method | Stefan | 1 | 1 | 0
10 | Draw a sketch of the register interface | Atanas | 1 | 0 | 0
10 | Code the Register GUI | Atanas | 3 | 0 | 0
10 | Code the Log In GUI | Atanas | 2 | 1 | 0
10 | Design a solution to interconnect logIn, Register and main user's interfaces | Atanas | 2 | 1 | 0
10 | Test connection | Atanas | 1 | 1 | 0
12 | User can log in with a username and password |  | 7
12 | Create a query to get a user's password | Daniel | 2 | 0 | 0
12 | Code the query which checks a username's availability | Daniel | 2 | 0 | 0
12 | Design a method which compares user input with data from the database | Daniel | 1 | 0 | 0
12 | Test log in | Daniel | 1 | 1 | 0
12 | Interconnect register, logIn and main GUIs | Daniel | 1 | 5 | 0
11 | User is able to change information in the profile |  | 5
11 | Code the Profile GUI | Atanas | 3 | 1 | 0
11 | Design a solution to create a User object from the values in Profile | Atanas | 1 | 1 | 0
11 | Test: create a new User object | Atanas | 1 | 1 | 0

## Sprint7
Sprint 7
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
18
2 | User can see a list of today's events |  | 18
2 | Normalize the relational database to third normal form | Atanas | 5 | 0 | 0
2 | Update the shared interface | Atanas | 2 | 0 | 0
2 | Update JDBC | Daniel | 3 | 1 | 0
2 | Update the Implementation class | Daniel | 5 | 7 | 0
2 | Update the history GUI | Daniel | 3 | 0 | 0
2 | Document all changes | Atanas | 4 | 0 | 0

## Sprint8
Sprint 8
StoryID | ITEM DESCRIPTION | Responsible | Estimation | Day 1 | Day 2
10
8 | All tickets are evaulated according to match results |  | 8
8 | Design a method to check the status of all matches in the ticket | Stefan | 4 | 0 | 0
8 | Method that sets ticket results | Stefan | 2 | 3 | 0
8 | Create a method, which edits a ticket's status in the database | Stefan | 2 | 2 | 0
9 | Winnings are distributed |  | 2
9 | When the ticket status is "Win", score is added to the user | Stefan | 2 | 0 | 0